HOSPITAL 360

Strategic Healthcare Management & Analytics Model

Complete 12-Step Practical Project Execution Guide

Locked project assumptions: Kangra–Palampur corridor, Himachal Pradesh | 100-bed multispecialty hospital | ₹50 crore Base Case | Hypothetical academic strategic model.

# STEP 1 — PROJECT FOUNDATION

Define exactly what Hospital 360 is solving. Prepare the project charter with title, problem statement, objectives, scope, assumptions, stakeholders, research questions and methodology.

FORMAT / FILES:

Word: Hospital_360_Project_Charter.docx

Excel sheet: 01_Project_Charter

Excel sheet: 02_Assumptions

Output: a clear project definition and assumption register.

# STEP 2 — HIMACHAL HEALTHCARE MARKET ANALYSIS

Collect official Himachal healthcare data, district population/catchment data, public healthcare infrastructure and relevant private-sector information. Separate every number into Actual Public Data, Benchmark, Assumption or Calculated Value.

FORMAT / FILES:

Excel sheet: 03_Himachal_Market_Data

Word: Hospital_360_HP_Market_Analysis.docx

Excel/Word: Source Register

Output: evidence-based market opportunity and gap analysis.

# STEP 3 — LOCATION FEASIBILITY

Evaluate the locked Kangra–Palampur corridor using transparent weighted criteria: catchment, accessibility, healthcare ecosystem, competition, referral potential, infrastructure and expansion potential. Use 1–5 scoring with documented weights.

FORMAT / FILES:

Excel sheet: 04_Location_Analysis

Word: Location_Feasibility_Notes.docx

Optional: Location_Map.png

Output: location scorecard and rationale. Do not claim site-level feasibility without detailed due diligence.

# STEP 4 — HOSPITAL BUSINESS & SERVICE MODEL

Define the 100-bed regional multispecialty concept, customer segments, value proposition, channels, revenue streams, key resources, partners and cost structure. Build Phase 1, Phase 2 and demand-driven Phase 3 services.

FORMAT / FILES:

Word: Hospital_360_Service_Model.docx

Excel sheet: 05_Hospital_Profile

Output: Business Model Canvas + service portfolio + strategic positioning.

# STEP 5 — CAPACITY & INFRASTRUCTURE

Build bed mix, OPD rooms, emergency, ICU/HDU, OT, maternity, diagnostics, pharmacy, CSSD, blood-support model, support departments, IT, built-up area, land planning and zoning. Keep the 100-bed model but launch with approximately 75–80 operational beds.

FORMAT / FILES:

Excel sheets: 06_Hospital_Design, 07_Bed_Mix, 08_Department_Planning

Optional: Hospital_Layout.png

Output: capacity plan, department plan and conceptual zoning.

# STEP 6 — HUMAN RESOURCE & MANPOWER MODEL

Build department-wise manpower for doctors, nursing, allied health, administration, quality, IT/MIS and support services. Separate launch, stabilisation and mature staffing. Use workload/productivity logic and a 15% reserve for leave/training where appropriate.

FORMAT / FILES:

Excel sheet: 09_Manpower

Word: Manpower_Assumptions.docx

Optional: Organisation_Chart.png

Output: manpower matrix, organisation structure and FTE assumptions.

# STEP 7 — FINANCIAL FEASIBILITY MODEL

Build the ₹50 crore Base Case with Lean ₹40 crore and Upper ₹60 crore scenarios. Model CAPEX, OPEX, revenue, P&L, cash flow, break-even, occupancy, ROI/ROCE, payback and sensitivity. Clearly mark all financial inputs as assumptions or benchmarks.

FORMAT / FILES:

Excel sheets: 10_CAPEX, 11_OPEX, 12_Revenue, 13_P&L, 14_Cash_Flow, 15_Break_Even, 16_Sensitivity

Output: integrated financial model and Go/No-Go decision logic.

# STEP 8 — HOSPITAL OPERATIONS MANAGEMENT

Map patient flow from entry to follow-up. Create OPD, emergency, bed management, discharge, OT, diagnostics, pharmacy, inventory, CSSD and daily huddle processes. Define internal operational targets and KPI formulas.

FORMAT / FILES:

Word: Hospital_360_Operations_SOP.docx

Excel sheets: 17_Operations_KPIs, 18_Patient_Flow

Output: operational blueprint, SOP framework and KPI catalogue.

# STEP 9 — QUALITY & NABH ROADMAP

Create a NABH-oriented quality framework covering AAC, COP, MOM, PRE, HIC, PSQ, ROM, FMS, HRM and IMS. Build committee structure, incident reporting, RCA/CAPA, quality indicators, readiness scoring and a 12-month implementation roadmap.

FORMAT / FILES:

Excel sheet: 19_NABH_Readiness

Word: Quality_Framework.docx

Output: quality framework and NABH readiness roadmap. State accreditation as a target, not a guarantee.

# STEP 10 — COMPETITOR BENCHMARKING

Benchmark Fortis Hospital Kangra, RPGMC Tanda, Zonal Hospital Dharamshala, Civil Hospital Palampur and relevant private/regional providers. Compare clinical capability, emergency, diagnostics, specialty breadth, patient experience, accessibility, digital capability, operational efficiency and reputation.

FORMAT / FILES:

Excel sheet: 20_Competitor_Benchmark

Excel: Competitor_Source_Register.xlsx

Output: competitor scorecard and differentiated positioning. Use 'Hospital 360 analytical assessment' rather than claiming official ratings.

# STEP 11 — HEALTHCARE ANALYTICS & POWER BI

Create synthetic/de-identified academic data for OPD, IPD, emergency, beds, OT, diagnostics, pharmacy, revenue, quality and HR. Build a star-schema model and Power BI dashboards for executive, patient flow, capacity, emergency/OT, diagnostics/pharmacy, HR, quality and finance.

FORMAT / FILES:

Excel: Hospital_360_Synthetic_Data.xlsx

Power BI: Hospital_360_PowerBI.pbix

Excel sheets: 21–32 Analytics

Output: dashboard showing Data → KPI → Insight → Decision → Action → Improvement.

# STEP 12 — FINAL STRATEGY & MANAGEMENT BLUEPRINT

Combine the evidence, location, service model, capacity, manpower, finance, operations, quality, competitors, analytics and risks into one strategic recommendation. Use CONDITIONAL GO as the default decision until site, demand, regulatory and financial due diligence are completed.

FORMAT / FILES:

Word: Hospital_360_Final_Report.docx

PowerPoint: Hospital_360_Final_Presentation.pptx

Word: Hospital_360_Final_Strategy.docx

Final recommendation: 100-bed regional multispecialty hospital in Kangra–Palampur, launched at 75–80 beds, ₹50 Cr Base Case, NABH-oriented systems and Power BI management layer.

# MASTER OUTPUT PACKAGE

Hospital_360_HP_Master_Model.xlsx

Hospital_360_Source_Register.xlsx

Hospital_360_Synthetic_Data.xlsx

Hospital_360_PowerBI.pbix

Hospital_360_Final_Report.docx

Hospital_360_Final_Presentation.pptx

Hospital_360_Project_Charter.docx

Hospital_360_Final_Strategy.docx

# RECOMMENDED FOLDER STRUCTURE

HOSPITAL 360
├── 01_Project_Foundation
├── 02_Market_Analysis
├── 03_Location_Feasibility
├── 04_Service_Business_Model
├── 05_Capacity_Infrastructure
├── 06_Manpower
├── 07_Financial_Model
├── 08_Operations
├── 09_NABH_Quality
├── 10_Competitor_Benchmark
├── 11_Analytics_PowerBI
├── 12_Final_Strategy
├── Hospital_360_HP_Master_Model.xlsx
├── Hospital_360_Source_Register.xlsx
├── Hospital_360_Synthetic_Data.xlsx
├── Hospital_360_PowerBI.pbix
├── Hospital_360_Final_Report.docx
└── Hospital_360_Final_Presentation.pptx

# FINAL 15-SLIDE PRESENTATION

1. Title & Project Concept

2. Problem Statement & Objectives

3. Himachal Healthcare Market

4. Kangra–Palampur Location Feasibility

5. Hospital Business Model

6. 100-Bed Capacity & Infrastructure

7. Manpower Model

8. ₹50 Cr Financial Model

9. Hospital Operations & Patient Flow

10. NABH-Oriented Quality Framework

11. Competitor Benchmark

12. Healthcare Analytics Architecture

13. Power BI Dashboard

14. Risks, Mitigation & Expansion Triggers

15. Final Strategy & Conditional Go/No-Go

# EXECUTION ORDER — DO NOT SKIP

Research → Source Register → Assumptions → Excel Master Model → Word Interpretation → Power BI → Final Report → Final Presentation.

Every number must be labelled Actual Public Data, Benchmark, Assumption or Calculated Value. Synthetic data must be explicitly labelled as synthetic and must never be presented as real patient/hospital data.